## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | Loc | In Charge | Status | Start date | End date | Actual | Updated | Update Details
2 | Home Page | Public | All | Show sliders, hot posts, featured services + the sider with the latest posts, static contacts/links - Shown slider information includes its image and title; the user is redirected to the slider's backlink on his/her clicking - Shown post information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clicking - Shown service information includes its thumbnail, title, brief information; the user is redirected to the service's details on his/her clicking | 120 | Chính | Done | 2023-09-10 | 2023-09-29 | iter1 | none
3 | User Register | Common | Guest | Allows the user to register to the system by inputing following information: full name, gender (Male, Female), email, mobile, user name, login password, confirm password; User then needs to verify by clicking the link sent via email to him/her before being able to access the system | 60 | Chính | Done | 2023-09-13 | 2023-09-22 | iter1 | none
4 | User Login | Common | Guest | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also options for user to register new information or reset the password for the case s/he forget it | 60 | Chính | Done | 2023-09-15 | 2023-09-25 | iter1 | none
5 | User Profile | Common | Guest | This is a pop-up screen which allows the user to edit his/her profile information, including the registered ones & the avatar image. Please note that s/he is not allowed to change the email | 60 | Chính | Done | 2023-09-17 | 2023-10-07 | iter1 | none
6 | User Authorization | Common | Guest | Implementation of authorization mechanism in the system, including the specify the role of logged-in user, his/her authorized page links (building the displayed menu items (in the front end) and preventing unauthorized access via enter the links directly) | 240 | Mạnh | Doing | 2023-09-10 | 2023-09-24 | iter1 | none
7 | Reset Password | Common | Guest | The user input his/her email to receive the reset password link. This link is sent to the user's email for his/her password resetting. - On clicking the link, the user is redirected to the password resetting page in which s/he input new password (twice) for the system access - Note that the link is only available for a specific time duration as configured in the system config file. | 120 | Chính | Done | 2023-09-27 | 2023-10-07 | iter2 | none
8 | Change Password | Common | Guest | This is a pop-up screen which allows the user to change his/her password by inputting his current password as well as new password (twice) | 60 | Chính | Done | 2023-09-28 | 2023-10-09 | iter2 | none
9 | Services List | Public |  | Show the services paginatedly (sorted by updated date, paginated) + the sider with the service search box, service types, static contacts/links; - Shown service information includes its thumbnail, title, brief information, original price, and sale price; - The user is redirected to the service's details on his/her clicking on the service - The user can choose to add the service to the cart or to feedback on the service by clicking the service's Buy & Feedback buttons responsively | 240 | Chính | Doing | 2023-10-09 |  | iter2
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SDS | Notes
1 | Create database, ERD | Database | Database design | MạnhVD | Doing | Doing
2 |  |  | Code DB
3 | Screen/Function Name2 | Enviroment | Project Create | ChínhNDD | Done
Github Document
5 | Screen/Function Name | Document | Đọc yêu cầu chi tiết | CảnhVD | Doing | Pending
6
7
8
9
10
11
12

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4

## Issue
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Running/Coding environment | Installed tool/kit/environment are not working properly in some members' pc |  |  | Open | ManhVD | 2023-09-08 |  | iter1 | Doing